## Roadmap
|  |  |  | R17 |  |  |  |  | R18 |  |  |  | L3 |  |  |  |  | AML
Workstreams | Milestones | PIC | Respnsible PIC | R17 Status | Start Date | Target Date | Actual Date | #of Resources | R18 Status | R18 Target Date | R18 Actual Date | Comments | L3 Status | L3 Start Date | L3 Target Date | L3 Actual Date | L3 #of Resources | AML Status | AML Start Date | AML Target Date | AML Actual Date | AML #of Resources
Program Milestones | Branch - Off | Chongyu |  | Not Applicable |  |  |  |  | Not Started | 2026-05-22
| Integration Complete | [7 empty] | Not Started | 2026-05-25
| SW Pre-Freeze | [7 empty] | Not Started | 2026-06-08
| SW Freeze / Harlock | [7 empty] | Not Started | 2026-06-19
| SW Freeze Mgmt Review | [7 empty] | Not Started | 2026-06-24
| RPD | [7 empty] | Not Started | 2026-07-20
VIP & Integration Milestones | VIP R18.0.0 |  |  | Not Started |  |  |  |  | In Progress |  |  | AA + Aurix Head (watchdog fixes for ST3 and parity to ST35 R17 parity ~4/9), HFE SILC/LC enhancements, FSI 04.00.00.10 (7% core savings), AVOS 65v4.9 (DRAM opt of ~450MB, RVC opts, …)
| SIT VIP acceptance | Robert Miles | Robert Miles | [5 empty] | In Progress | 2026-04-17 |  | 3 Days of testing: Includes Driving/Parking/Active Safety. Dependent on weekend resourcing availability. Any change in timeline will affect consecutive timelines in rows 12-15
| PMB Shadow Mode Acceptance | Pavi | Pavi | [5 empty] | Not Started | 2026-04-21
| Exec car updrade | Johnny Chi | Johnny | [5 empty] | Not Started | 2026-04-24
| Mini CCB | Jisha/Pavi | [6 empty] | Not Started | 2026-04-24
| PMB Cars Upgraded | Johnny Chi US | Johnny | [5 empty] | Not Started | 2026-04-29 |  | pending VIT resourcing + Config finalized
| California Cars Upgraded | Johnny Chi US | [9 empty] | ~2.5w to convert pending VIT resourcing + Config finalized + feasibility to down cars
| Remote/Sweeping Cars Upgraded | Johnny Chi US | [9 empty] | pending VIT resourcing + Config finalized + feasibility to down cars
| VIP R18.1.0 | [7 empty] | Not Started | 2026-04-21 |  | Original MB Release Target Date: 4/17/2026 Fixes over R18.0.0 from PRE-INT testing (will go wider based on stability) + FSI .11 + DEXT + NCD
| SIT VIP acceptance | Robert Miles | [6 empty] | Not Started | 2026-04-29 |  | Best case if R18 BC Car gets allocated
| PMB Shadow Mode Acceptance | Pavi | [6 empty] | Not Started | 2026-05-01 |  | Vehicle needs to allocated and Updated to PMB for Shadow
| Exec car updrade | Johnny Chi | [6 empty] | Not Started | 2026-05-05
| Mini CCB | Jisha/Pavi | [6 empty] | Not Started | 2026-05-05
| PMB Cars Upgraded | Johnny Chi US | [6 empty] | Not Started |  |  | pending VIT resourcing + Config finalized
| California Cars Upgraded | Johnny Chi US | [9 empty] | pending VIT resourcing + Config finalized + feasibility to down cars
| Remote/Sweeping Cars Upgraded | Johnny Chi US | [9 empty] | pending VIT resourcing + Config finalized + feasibility to down cars
Platform - Feature Milestones |  | Tao Xie | [6 empty] | Not Applicable
Product - Feature Milestones | L2 Driving - L2p Planner FC | Kyle Olive | [6 empty] | In Progress | 2026-04-27
| Feature in PMB | Kyle Olive | [6 empty] | In Progress | 2026-04-27
| VIP XXX Acceptance & Approval | Robert | [6 empty] | In Progress
| Car Allocation | Toan/Johnny
| Car Provisioning | Kellen
| Test Plan | Renmin | [6 empty] | In Progress | 2026-04-27
| KPI | Triage | [6 empty] | In Progress
| Maps | [7 empty] | Not Applicable
| Regions / Hubs | [7 empty] | Not Applicable
| PMB Digital Replay Test Enablement | Amit | [6 empty] | In Progress
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started
| L2pp - AMO FC | Shai | [6 empty] | In Progress | 2026-04-27
| L2PP CA Sweeping | @JunLin Liu | [6 empty] | In Progress | 2026-04-26
| L2PP - TX Sweeping | @JunLin Liu | [6 empty] | In Progress | 2026-06-07
| L2PP - NJ/NY Sweeping | @JunLin Liu | [6 empty] | Not Started | 2026-07-12
| Feature in PMB | Shai | [6 empty] | In Progress | 2026-04-27
| VIP XXX Acceptance & Approval | Robert | [6 empty] | In Progress
| Car Allocation | Toan/Johnny
| Car Provisioning | Kellen
| TO Allocation | [7 empty] | Not Applicable
| Test Plan | Renmin | [6 empty] | In Progress | 2026-04-27
| KPI | Jason | [6 empty] | In Progress
| Maps CA | Frank | [6 empty] | In Progress
| Maps TX | Frank | [6 empty] | In Progress
| Maps NJ | Frank | [6 empty] | In Progress
| Regions / Hubs - VnV Testing | @JunLin Liu | [6 empty] | In Progress | 2026-07-12 |  | Same as sweeping timelines
| PMB Digital Replay Test Enablement | Amit | [6 empty] | In Progress
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started
| Highway AMO + HFE | Marcus Sjolin |  | Not Applicable |  |  |  |  | In Progress
| Feature in PMB | Ninad | [6 empty] | In Progress | 2026-04-27
| VIP R18.X.X Readiness | Robert Miles | [6 empty] | Provisional | 2026-04-19 |  | Manual coding being used. Waiting on an official VIP.
| Official VIP | Robert Miles | [6 empty] | Not Started | 2026-04-20
| DAG/Config Updates | Xiao Bo | [6 empty] | In Progress | 2026-04-27
| Car Allocation | Johnny Chi | [6 empty] | Complete
| Car Provisioning | Prachin Anne | [6 empty] | Complete
| TO Allocation | Jingyi Chen | [6 empty] | Not Applicable
| Test Plan | Ninad Alulkar | [6 empty] | In Progress | 2026-04-27
| KPI | Jason | [6 empty] | In Progress
| Triage | Ketaki Kher IN | [6 empty] | In Progress
| Alfred enablement | Luke Wang | [6 empty] | In Progress
| KPI Computation | Luke Wang | [6 empty] | Not Started
| Maps | Fan Wu (Automotive) CN | [6 empty] | In Progress | 2026-04-20
| Regions / Hubs | PJ Casey | [6 empty] | In Progress | 2026-04-24
| PMB Digital Replay Test Enablement | Gaurav Ahuja | [6 empty] | In Progress | 2026-04-24 |  | HFE availability, Curvature in open loop - 4/17/2026 HFE AMO CLE depends on Nurec update.
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started | 2026-04-29
| Highway AMO + SILC | Sourav Pramanik | [6 empty] | In Progress | 2026-04-27 |  | Paolo for AMO Hwy and Sourav for AMO Hwy SILC
| Feature in PMB | Vinay Kaitha | [6 empty] | Complete | 2026-03-24
| VIP R18.X.X Readiness | [7 empty] | Not Applicable
| 8 cam compatibility | [7 empty] | Not Started
| 10 cam compatibility | [7 empty] | Complete
| Car Allocation | [7 empty] | Complete
| Car Provisioning | [7 empty] | Not Applicable
| TO Allocation | [7 empty] | Complete
| Test Plan | Vinay Kaitha | [6 empty] | Complete
| Diversity Drives | Siddharth | [6 empty] | Not Started | 2026-04-15
| KPI | Luke Wang | [6 empty] | In Progress
| Maps | [7 empty] | Not Applicable
| Regions / Hubs | PJ Casey | [6 empty] | Complete
| PMB Digital Replay Test Enablement | Gaurav Ahuja | [6 empty] | Not Started | 2026-04-24 |  | Nurec at high speed does not have good quality. 500 tests have been created but are flaky. Waiting on update on the Nurec side.
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started
| DCAS | Kaiyuan Wei |  | Not Applicable |  |  |  |  | In Progress
| Feature in PMB | [7 empty] | Blocked | 2026-04-27
| VIP XXX Acceptance & Approval | [7 empty] | In Progress | 2026-04-27
| R18 Vehicle Resource Allocation | [7 empty] | Complete
| Car Provisioning | [7 empty] | Not Started
| TO Allocation | [7 empty] | Not Started
| Test Plan | Karthik P | [6 empty] | Not Started
| KPI | [7 empty] | Not Started
| Maps | [7 empty] | In Progress
| Regions / Hubs | [7 empty] | In Progress
| PMB Digital Replay Test Enablement | Gaurav Ahuja | [6 empty] | Not Started
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started
| Highway AMO + HFE + SILC | [7 empty] | In Progress
| Feature in PMB | [7 empty] | Blocked | 2026-04-27 |  | R18.0.0
| VIP XXX Acceptance & Approval | [7 empty] | In Progress | 2026-04-27
| R18 Vehicle Resource Allocation | [7 empty] | Complete
| Car Provisioning | [7 empty] | Not Started
| TO Allocation | [7 empty] | Not Started
| Test Plan | [7 empty] | Not Started
| KPI | [7 empty] | Not Started
| Maps | [7 empty] | In Progress
| Regions / Hubs | [7 empty] | In Progress
| PMB Digital Replay Test Enablement | [7 empty] | Not Started
| PMB Digital Replay Test Execution | [7 empty] | Not Started
| Parking (APA) | Kevin Jin | [6 empty] | In Progress
| EGM v10.3 | [7 empty] | In Progress | 2026-03-20
| IBEV EGM v11 | [7 empty] | Not Started | 2026-04-30
| EGM v11 | [7 empty] | Not Started | 2026-05-29
| ParkNet v13 | [7 empty] | Not Started | 2026-05-29
| PMB Build ready | [7 empty] | In Progress
| VIP XXX Acceptance & Approval | [7 empty] | Not Applicable
| Car Allocation | Toan/Johnny
| Car Provisioning | VIT | [6 empty] | Not Started
| TO Allocation | Ops | [6 empty] | Not Started
| Test Plan | Vivek | [6 empty] | In Progress
| KPI | [7 empty] | Not Started
| Maps | [7 empty] | Not Applicable
| Regions / Hubs | [7 empty] | Not Applicable
| PMB Digital Replay Test Enablement | Neha
| PMB Digital Replay Test Execution | Neha
| L2PP CA | [7 empty] | Not Applicable | 2026-04-26
| L2PP - TX | [7 empty] | Not Applicable | 2026-06-07
| L2PP - NJ/NY | [7 empty] | Not Applicable | 2026-07-12
| PMB Build | [7 empty] | In Progress | 2026-06-19
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
| PMB Digital Replay Test Enablement | [7 empty] | In Progress
| PMB Digital Replay Test Execution | [7 empty] | In Progress
PMB Build
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
PMB Digital Replay Test Enablement
PMB Digital Replay Test Execution
| Active Safety (AS) | Edozie Eze | [6 empty] | In Progress
| LSS - Steering angle limit, V_lat at return (Risk; NCAP 2026) | [7 empty] | In Progress | 2026-03-20
| Improve sensitivity to driver steering / AES robustness (NCAP 2026) | [7 empty] | In Progress | 2026-03-20
| BSM to consume ASMSF | [7 empty] | In Progress | 2026-04-01
| AES - AEB co-actuation TBD | [7 empty] | In Progress | 2026-04-10
| BSM Fusion enablement | [7 empty] | In Progress | 2026-04-10
| 4/13 [NCAP] Baseline on 167, 223 | [7 empty] | In Progress | 2026-04-13
| Polar model v6 (NCAP 2026): AEB robustness w/ pitch change; MBVans FN; AEB/CPM FP suppression | [7 empty] | In Progress | 2026-04-15
| 4/27 [NCAP] Spot check on vans | [7 empty] | In Progress | 2026-04-27
| BSM/DOW w/ trailer KPI improvements (Risk) | [7 empty] | In Progress | 2026-04-27
| BSM/DOW w/ trailer Feature Enablement Only (Risk) | [7 empty] | In Progress | 2026-05-01
| AES/LSS improved availability (NCAP 2026) | [7 empty] | In Progress | 2026-05-15
| BSM/DOW w/ trailer (Risk) | [7 empty] | In Progress | 2026-05-20
| Feature MF5 | [7 empty] | In Progress | 2026-05-29
| P&C Planner tuning for NCAP 2026 | [7 empty] | In Progress | 2026-06-01
PMB Build ready
VIP XXX Acceptance & Approval
| Car Allocation | [7 empty] | Not Applicable
| Car Provisioning | [7 empty] | Not Applicable
| TO Allocation | [7 empty] | Not Applicable
| Test Plan | [7 empty] | Not Applicable
| KPI | [7 empty] | Not Applicable
| Maps | [7 empty] | Not Applicable
| Regions / Hubs | [7 empty] | Not Applicable
| PMB Digital Replay Test Enablement | [7 empty] | Not Started
| PMB Digital Replay Test Execution | [7 empty] | Not Started
PMB Branching | Branch Off | Adam Watson |  | Not Started |  |  |  |  | Not Started | 2026-05-22
| Daily Build Starts | [7 empty] | Not Started | 2026-05-23
| Branch Fast Forward | Frank Bourgeois US | [6 empty] | Not Started | 2026-05-22
| Main Freeze | Adam Watson US | [6 empty] | Not Started | 2026-05-20
| GVS Compute Allocation | Sam Payne US | [6 empty] | Not Started | 2026-05-20
| Alfred Setup | Yancy Tao | [6 empty] | Not Started | 2026-05-20
| Automatic PMB Setup | Adam Watson US | [6 empty] | Not Started | 2026-05-20
| QC Support | Sagar Udasi IN | [6 empty] | Not Started | 2026-05-20
| Maintainer Support | Udith Hegde US | [6 empty] | Not Started | 2026-05-20
| AVBT Checklist | Frank Bourgeois US | [6 empty] | Not Started | 2026-05-15
| CCB Setup | Ying Ying US | [6 empty] | Not Started | 2026-05-19
| DIFORV Setup | Keshav Aggarwal IN | [6 empty] | Not Started | 2026-05-18
| MTTF Setup | Andrew Hu CN | [6 empty] | Not Started | 2026-05-18
| Promotions Setup | Frank Bourgeois US | [6 empty] | Not Started | 2026-05-17
| Config List | Doug Seay US |  | Not Started |  |  |  |  | Not Started | 2026-05-15
| Branch Activation | Frank Bourgeois US | [6 empty] | Not Started | 2026-05-15
Car Demand Planning | Car Prioiritization | Toan Do | Johnny Chi | Not Started |  |  |  |  | In Progress | 2026-04-17
Ops | Dispatch & Scheduling | Anna Svizhenko | Eric Estes | Not Started
| TO Allocation | Jingyi Chen | Frederick Yen | Not Started
| TO Annotation, Guidelines and Training | Elizabeth Busi |  | Not Started
| Exec Drives Scheduling | Jingyi Chen | Frederick Yen | Not Started
| Car Provisioning | Kellen Davies |  | Not Started | [5 empty] | 2026-04-27
| MTTF Provisioning | Kellen Davies
| US: Scaling PMB: HFE + AMO Highway | Jenny Liu | [6 empty] | Blocked | 2026-05-04 |  | Pending Test Requirements and Test Plan Review Ninad Alulkar US, Vinay Kumar Reddy Kaitha US.
In Car Testing Strategy | Test Plan & Strategy | Bruce Guo | Amol Wandile | In Process |  |  |  |  | Complete |  |  | [SIT] R18 Test Plan & Strategy Diversity plan aligning with V&V and DA
| Test Execution Plan | Renmin/Vinay/Ninad | [6 empty] | In Progress | 2026-04-27 |  | R18 [Carline][L2++ Safety][Pre-Merge] in progress
| Diversity Test Plan | Renmin/Vinay/Ninad | [6 empty] | In Progress | 2026-04-22 |  | R18 L2+ & HFE US Freeway Driving Validation Plan0
| PMB Test Start in US & EU | Bruce Guo | [6 empty] | Complete | 2026-03-20
| IFORV | Dhiraj
| Maps | Clint May |  | Not Started
| Regions/Hubs | Bruce Guo | Amol Wandile | Not Started |  |  |  |  | In Progress |  |  | diversity plan align with V&V
Offline Testing | Digital Replay Component WFs | Kelly Clonts |  | Not Started |  |  |  |  | In Progress
| DIFORV | Gaurav Ahuja | Jisha Prakash | Not Started |  |  |  |  | In Progress
| AMO CLE | Kelly Clonts | Michael Kasa | Not Started |  |  |  |  | In Progress
| HCM | Kelly Clonts | James Schulmeister | Not Started |  |  |  |  | In Progress
| Perf Test Suote | Sai Gurrappadi
| Release WF | Gaurav Ahuja | Vikas Jethlya | Not Started
| SIL3 | Jay Cheng | Pradyotha Nori | Not Started
| MTTF Allocation | Houman Tavakoli | Sreekanth Vietla | Not Started |  |  |  |  | Complete
| MTTF Execution | Dhanakodi Prabhu | Rahul Bahirmal | [5 empty] | In Progress
| Car CI/STS Suite | Hunk Lin | Richard Lin | Not Started |  |  |  |  | Complete
| Car CI/STS Execution | Dhanakodi Prabhu | Rahul Bahirmal | [5 empty] | In Progress
Post Drive Gates | Perf | Sai Gurrappadi | Eli Feinberg | Not Started |  |  |  |  | In Progress
| DI/DQ | Karthik Bhardwaj |  | Not Started
| Exceptions | Thomas Rushton |  | Not Started
Triage | Tagging Definitions | Jason Xiao | [6 empty] | In Progress
KPI Tracking
In Progress
Tooling | Alfred | Hunk Lin |  | Not Started |  |  |  |  | Not Started
Test Studio
Quality Control (QC)
OPTIC
| Optic | Keshav Agarwal | [6 empty] | In Progress

## Program Milestones
Milestones | Level | Workstream | PIC | Status | Start Date | ETC | Actual Completion | Dependency | Comments
Product Feature Completion | L1 | Product | Kyle | In Progress | 2026-04-24 | 2026-04-24
R18.0.0 VIP | L1 | Sys Int | Todd | In Progress |  | 2026-04-24
R18.1.0 VIP | L1 | Sys Int | Todd | Not Started |  | 2026-05-05
R18 x.x.x VIP | L1 | Sys Int | Todd | Not Started |  | 2026-05-22
LKG Pre RC VIP | L1 | Sys Int | Todd | Not Started |  | 2026-06-12
Zero Rel Blockers | L1 | Sys Int | Todd | Not Started |  | 2026-06-19
Complete Fleet Transition to R18.0.0 VIP | L1 | Car Prioritization/Diversity | Toan | Blocked |  | 2026-04-29 |  | R18.0.0 VIP Approval
L2PP Sweeping CA | L1 | InCar Testing | Bruce | In Progress |  | 2026-04-26
L2PP Sweeping TX | L1 | InCar Testing | Bruce | In Progress |  | 2026-06-07
L2PP Sweeping NJ | L1 | InCar Testing | Bruce | Not Started |  | 2026-07-12
Sweeping - VnV Testing Completion | L1 | InCar Testing | Bruce | In Progress |  | 2026-07-12
PMB/Scaling / Diversity Test Plan Strategy | L1 | InCar Testing | Bruce | In Progress |  | 2026-04-22
PMB/Scaling / Diversity Test Execution Plan | L1 | InCar Testing | Bruce | In Progress |  | 2026-04-27 |  |  | R18 [Carline][L2++ Safety][Pre-Merge]
USA Scaling (Diversity Tier1/Tier2 ) Testing Completion | L1 | Car Prioritization/Diversity | Toan | Blocked |  | 2026-05-04 |  | -PMB/Scaling / Diversity Test Plan Strategy -PMB/Scaling / Diversity Test Execution Plan | Pending Test Requirements and Test Plan Review Ninad Alulkar US, Vinay Kumar Reddy Kaitha US.
R18 PMB Branch Off & Process | L1 | PMB | Gaurav | Blocked |  | 2026-05-22 |  | Product Feature Completion
Integration Complete | L1 | Program | Moore | Blocked |  | 2026-05-25 |  | R18 PMB Branch Off
SW Pre-Freeze | L1 | Program | Moore | Blocked |  | 2026-06-08 |  | Integration Complete
SW Freeze / Harlock | L1 | Program | Moore | Blocked |  | 2026-06-19 |  | SW Pre-Freeze
SW Freeze Mgmt Review | L1 | Program | Moore | Blocked |  | 2026-06-24 |  | SW Freeze / Harlock
RPD | L1 | Program | Moore | Blocked |  | 2026-07-20 |  | SW Freeze Mgmt Review
Highway AMO SILC Feature in PMB | L2 | Product | Sourav Pramanik | Complete
Highway AMO SILC PMB Test Plan Complete | L2 | InCar Testing | Vinay | In Progress |  | 2026-04-27
Highway AMO SILC DAG /Config Updates | L2 | Product | Xiao Bo | In Progress
Highway AMO SILC Digital Replay Testing Enablement | L2 | PMB | Amit | Not Started |  | 2026-04-24
HFE Feature in PMB | L2 | Product | Marcus Sjolin | In Progress |  | 2026-04-24
HFE Test Plan Complete | L2 | InCar Testing | Ninad | In Progress |  | 2026-04-27
HFE DAG/Config Updates | L2 | Product | Xiao Bo | In Progress
HFE Digital Replay Testing Enablement | L2 | PMB | Amit | In Progress |  | 2026-04-24
DCAS Feature in PMB | L2 | Product | Kaiyuan Wei | Blocked |  | 2026-04-27
DCAS PMB Test Plan Complete | L2 | InCar Testing | Karthik P | In Progress |  | 2026-04-27
DCAS DAG /Config Updates | L2 | Product | Xiao Bo | In Progress
APA P2P On Street Feature in PMB | L2 | Product | Edozie | In Progress
APA P2P On Street Test Plan Complete | L2 | InCar Testing | Saiprasad | In Progress
APA P2P On Street Digital Replay Testing Enablement | L2 | PMB | Amit | In Progress
Active Safety Feature in PMB | L2 | Product | Saiprasad | In Progress
Active SafetyTest Plan Complete | L2 | InCar Testing | Saiprasad | In Progress
ATCA Feature in PMB | L2 | Product
ATCA Test Plan Complete | L2 | InCar Testing
Branch Activation | L2 | PMB | Adam | Blocked |  | 2026-05-15 |  | Product Feature Completion
Config List | L2 | PMB | Adam | Blocked |  | 2026-05-15 |  | Product Feature Completion
Promotions Setup | L2 | PMB | Adam | Blocked |  | 2026-05-17 |  | Product Feature Completion
MTTF Setup | L2 | PMB | Adam | Blocked |  | 2026-05-18 |  | Product Feature Completion
DIFORV Setup | L2 | PMB | Adam | Blocked |  | 2026-05-18 |  | Product Feature Completion
CCB Setup | L2 | PMB | Adam | Blocked |  | 2026-05-19 |  | Product Feature Completion
AVBT Checklist | L2 | PMB | Adam | Blocked |  | 2026-05-15 |  | Product Feature Completion
Maintainer Support | L2 | PMB | Adam | Blocked |  | 2026-05-20 |  | Product Feature Completion
QC Support | L2 | PMB | Adam | Blocked |  | 2026-05-20 |  | Product Feature Completion
Automatic PMB Setup | L2 | PMB | Adam | Blocked |  | 2026-05-20 |  | Product Feature Completion
Alfred Setup | L2 | PMB | Adam | Blocked |  | 2026-05-20 |  | Product Feature Completion
GVS Compute Allocation | L2 | PMB | Adam | Blocked |  | 2026-05-20 |  | Product Feature Completion
Main Freeze | L2 | PMB | Adam | Blocked |  | 2026-05-20 |  | Product Feature Completion
Branch Fast Forward | L2 | PMB | Adam | Blocked |  | 2026-05-22 |  | Product Feature Completion
Daily Build Starts | L2 | PMB | Adam | Blocked |  | 2026-05-23 |  | Product Feature Completion
Formulas:
Start Date = [ETC]

## Draft_WG (hidden)
|  |  |  | R17 |  |  |  |  | R18 |  |  |  | L3 |  |  |  |  | AML
Workstreams | Milestones | PIC | Respnsible PIC | R17 Status | Start Date | Target Date | Actual Date | #of Resources | R18 Status | R18 Target Date | R18 Actual Date | Comments | L3 Status | L3 Start Date | L3 Target Date | L3 Actual Date | L3 #of Resources | AML Status | AML Start Date | AML Target Date | AML Actual Date | AML #of Resources
Program Milestones | Branch - Off | Chongyu |  | Not Applicable |  |  |  |  | Not Started | 2026-05-22
| Integration Complete | [7 empty] | Not Started | 2026-05-25
| SW Pre-Freeze | [7 empty] | Not Started | 2026-06-08
| SW Freeze / Harlock | [7 empty] | Not Started | 2026-06-19
| SW Freeze Mgmt Review | [7 empty] | Not Started | 2026-06-24
| RPD | [7 empty] | Not Started | 2026-07-20
VIP & Integration Milestones | VIP R18.0.0 |  |  | Not Started |  |  |  |  | In Progress |  |  | AA + Aurix Head (watchdog fixes for ST3 and parity to ST35 R17 parity ~4/9), HFE SILC/LC enhancements, FSI 04.00.00.10 (7% core savings), AVOS 65v4.9 (DRAM opt of ~450MB, RVC opts, …)
| SIT VIP acceptance | Robert Miles | Robert Miles | [5 empty] | In Progress | 2026-04-17 |  | 3 Days of testing: Includes Driving/Parking/Active Safety. Dependent on weekend resourcing availability. Any change in timeline will affect consecutive timelines in rows 12-15
| PMB Shadow Mode Acceptance | Pavi | Pavi | [5 empty] | Not Started | 2026-04-21
| Exec car updrade | Johnny Chi | Johnny | [5 empty] | Not Started | 2026-04-24
| Mini CCB | Jisha/Pavi | [6 empty] | Not Started | 2026-04-24
| PMB Cars Upgraded | Johnny Chi US | Johnny | [5 empty] | Not Started | 2026-04-29 |  | pending VIT resourcing + Config finalized
| California Cars Upgraded | Johnny Chi US | [9 empty] | ~2.5w to convert pending VIT resourcing + Config finalized + feasibility to down cars
| Remote/Sweeping Cars Upgraded | Johnny Chi US | [9 empty] | pending VIT resourcing + Config finalized + feasibility to down cars
| VIP R18.1.0 | [7 empty] | Not Started | 2026-04-21 |  | Original MB Release Target Date: 4/17/2026 Fixes over R18.0.0 from PRE-INT testing (will go wider based on stability) + FSI .11 + DEXT + NCD
| SIT VIP acceptance | Robert Miles | [6 empty] | Not Started | 2026-04-29 |  | Best case if R18 BC Car gets allocated
| PMB Shadow Mode Acceptance | Pavi | [6 empty] | Not Started | 2026-05-01 |  | Vehicle needs to allocated and Updated to PMB for Shadow
| Exec car updrade | Johnny Chi | [6 empty] | Not Started | 2026-05-05
| Mini CCB | Jisha/Pavi | [6 empty] | Not Started | 2026-05-05
| PMB Cars Upgraded | Johnny Chi US | [6 empty] | Not Started |  |  | pending VIT resourcing + Config finalized
| California Cars Upgraded | Johnny Chi US | [9 empty] | pending VIT resourcing + Config finalized + feasibility to down cars
| Remote/Sweeping Cars Upgraded | Johnny Chi US | [9 empty] | pending VIT resourcing + Config finalized + feasibility to down cars
Platform - Feature Milestones |  | Tao Xie | [6 empty] | Not Applicable
Product - Feature Milestones | L2 Driving - L2p Planner | Kyle Olive | [6 empty] | In Progress
| PMB Build | [7 empty] | Complete
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
PMB Digital Replay Test Enablement
PMB Digital Replay Test Execution
| L2pp - AMO | Drew Beller | [6 empty] | In Progress
| L2PP CA Sweeping | [8 empty] | 2026-04-26
| L2PP - TX Sweeping | [8 empty] | 2026-06-07
| L2PP - NJ/NY Sweeping | [8 empty] | 2026-07-12
| PMB Build | [7 empty] | In Progress | 2026-06-19
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
| PMB Digital Replay Test Enablement | [7 empty] | In Progress
| PMB Digital Replay Test Execution | [7 empty] | In Progress
PMB Build
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
PMB Digital Replay Test Enablement
PMB Digital Replay Test Execution
| Highway AMO + HFE | Marcus Sjolin |  | Not Applicable |  |  |  |  | In Progress
| Feature in PMB | Ninad | [6 empty] | Complete | 2026-03-20
| VIP R18.X.X Readiness | Robert Miles | [6 empty] | Provisional | 2026-04-19 |  | Manual coding being used. Waiting on an official VIP.
| Official VIP | Robert Miles | [6 empty] | Not Started | 2026-04-20
| 8 cam compatibility | Xiao Bo | [6 empty] | In Progress | TBD
| 10 cam compatibility | Xiao Bo | [6 empty] | Complete
| Car Allocation | Johnny Chi | [6 empty] | Complete
| Car Provisioning | Prachin Anne | [6 empty] | Complete
| TO Allocation | Jingyi Chen | [6 empty] | Complete
| Test Plan | Ninad Alulkar | [6 empty] | In Progress | 2026-04-27
| KPI | Ninad Alulkar | [6 empty] | In Progress
| Product KPI Definition | Marcus Sjolin /Jugal | [6 empty] | In Progress
| Triage | Ketaki Kher IN | [6 empty] | In Progress
| Alfred enablement | Luke Wang | [6 empty] | In Progress
| KPI Computation | Luke Wang | [6 empty] | Not Started
| Maps | Fan Wu (Automotive) CN | [6 empty] | In Progress | 2026-04-20
| Regions / Hubs | PJ Casey | [6 empty] | In Progress | 2026-04-24
| PMB Digital Replay Test Enablement | Gaurav Ahuja | [6 empty] | In Progress | 2026-04-24 |  | HFE availability, Curvature in open loop - 4/17/2026 HFE AMO CLE depends on Nurec update.
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started | 2026-04-29
| Highway AMO + SILC | Sourav Pramanik | [6 empty] | In Progress |  |  | Paolo for AMO Hwy and Sourav for AMO Hwy SILC
| Feature in PMB | Vinay Kaitha | [6 empty] | Complete | 2026-03-24
| VIP R18.X.X Readiness | [7 empty] | Not Applicable
| 8 cam compatibility | [7 empty] | Not Started
| 10 cam compatibility | [7 empty] | Complete
| Car Allocation | [7 empty] | Complete
| Car Provisioning | [7 empty] | Not Applicable
| TO Allocation | [7 empty] | Complete
| Test Plan | Vinay Kaitha | [6 empty] | Complete
| Diversity Drives | Siddharth | [6 empty] | Not Started | 2026-04-15
| KPI | Luke Wang | [6 empty] | In Progress
| Maps | [7 empty] | Not Applicable
| Regions / Hubs | PJ Casey | [6 empty] | Complete
| PMB Digital Replay Test Enablement | Gaurav Ahuja | [6 empty] | Not Started | 2026-04-24 |  | Nurec at high speed does not have good quality. 500 tests have been created but are flaky. Waiting on update on the Nurec side.
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started
| DCAS | Kaiyuan Wei |  | Not Applicable |  |  |  |  | In Progress
| Feature in PMB | [7 empty] | Blocked | 2026-04-27
| VIP XXX Acceptance & Approval | [7 empty] | In Progress | 2026-04-27
| R18 Vehicle Resource Allocation | [7 empty] | Complete
| Car Provisioning | [7 empty] | Not Started
| TO Allocation | [7 empty] | Not Started
| Test Plan | Karthik P | [6 empty] | Not Started
| KPI | [7 empty] | Not Started
| Maps | [7 empty] | In Progress
| Regions / Hubs | [7 empty] | In Progress
| PMB Digital Replay Test Enablement | Gaurav Ahuja | [6 empty] | Not Started
| PMB Digital Replay Test Execution | Dhanakodi Prabhu | [6 empty] | Not Started
| Highway AMO + HFE + SILC | [7 empty] | In Progress
| Feature in PMB | [7 empty] | Blocked | 2026-04-27 |  | R18.0.0
| VIP XXX Acceptance & Approval | [7 empty] | In Progress | 2026-04-27
| R18 Vehicle Resource Allocation | [7 empty] | Complete
| Car Provisioning | [7 empty] | Not Started
| TO Allocation | [7 empty] | Not Started
| Test Plan | [7 empty] | Not Started
| KPI | [7 empty] | Not Started
| Maps | [7 empty] | In Progress
| Regions / Hubs | [7 empty] | In Progress
| PMB Digital Replay Test Enablement | [7 empty] | Not Started
| PMB Digital Replay Test Execution | [7 empty] | Not Started
| Parking (APA) | Kevin Jin | [6 empty] | In Progress
| EGM v10.3 | [7 empty] | In Progress | 2026-03-20
| IBEV EGM v11 | [7 empty] | Not Started | 2026-04-30
| EGM v11 | [7 empty] | Not Started | 2026-05-29
| ParkNet v13 | [7 empty] | Not Started | 2026-05-29
| PMB Build ready | [7 empty] | In Progress
| VIP XXX Acceptance & Approval | [7 empty] | Not Applicable
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
PMB Digital Replay Test Enablement
PMB Digital Replay Test Execution
| L2PP CA | [8 empty] | 2026-04-26
| L2PP - TX | [8 empty] | 2026-06-07
| L2PP - NJ/NY | [8 empty] | 2026-07-12
| PMB Build | [7 empty] | In Progress | 2026-06-19
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
| PMB Digital Replay Test Enablement | [7 empty] | In Progress
| PMB Digital Replay Test Execution | [7 empty] | In Progress
PMB Build
VIP XXX Acceptance & Approval
Car Allocation
Car Provisioning
TO Allocation
Test Plan
KPI
Maps
Regions / Hubs
PMB Digital Replay Test Enablement
PMB Digital Replay Test Execution
| Active Safety (AS) | Edozie Eze | [6 empty] | In Progress
| LSS - Steering angle limit, V_lat at return (Risk; NCAP 2026) | [7 empty] | In Progress | 2026-03-20
| Improve sensitivity to driver steering / AES robustness (NCAP 2026) | [7 empty] | In Progress | 2026-03-20
| BSM to consume ASMSF | [7 empty] | In Progress | 2026-04-01
| AES - AEB co-actuation TBD | [7 empty] | In Progress | 2026-04-10
| BSM Fusion enablement | [7 empty] | In Progress | 2026-04-10
| 4/13 [NCAP] Baseline on 167, 223 | [7 empty] | In Progress | 2026-04-13
| Polar model v6 (NCAP 2026): AEB robustness w/ pitch change; MBVans FN; AEB/CPM FP suppression | [7 empty] | In Progress | 2026-04-15
| 4/27 [NCAP] Spot check on vans | [7 empty] | In Progress | 2026-04-27
| BSM/DOW w/ trailer KPI improvements (Risk) | [7 empty] | In Progress | 2026-04-27
| BSM/DOW w/ trailer Feature Enablement Only (Risk) | [7 empty] | In Progress | 2026-05-01
| AES/LSS improved availability (NCAP 2026) | [7 empty] | In Progress | 2026-05-15
| BSM/DOW w/ trailer (Risk) | [7 empty] | In Progress | 2026-05-20
| Feature MF5 | [7 empty] | In Progress | 2026-05-29
| P&C Planner tuning for NCAP 2026 | [7 empty] | In Progress | 2026-06-01
PMB Build ready
VIP XXX Acceptance & Approval
| Car Allocation | [7 empty] | Not Applicable
| Car Provisioning | [7 empty] | Not Applicable
| TO Allocation | [7 empty] | Not Applicable
| Test Plan | [7 empty] | Not Applicable
| KPI | [7 empty] | Not Applicable
| Maps | [7 empty] | Not Applicable
| Regions / Hubs | [7 empty] | Not Applicable
| PMB Digital Replay Test Enablement | [7 empty] | Not Started
| PMB Digital Replay Test Execution | [7 empty] | Not Started
PMB Branching | Branch Off | Adam Watson |  | Not Started | [5 empty] | 2026-05-22
Daily Build
Conflict Resolution
Respin
Promotions
| Config List | Doug Seay US |  | Not Started
| GVS Compute Allocation | Sam Payne US
| Alfred Setup | Yancy Tao
| Automatic PMB Setup | Adam Watson US
| QC Support | Sagar Udasi IN
| Maintainer Support | Udith Hegde US
| DIFORV Setup | Keshav Aggarwal IN
| MTTF Setup | Andrew Hu CN
| AVBT Checklist | Frank Bourgeois US
| CCB Setup | Ying Ying US
| Promotions Setup | Frank Bourgeois US
| Branch Activation | Frank Bourgeois US
| Branch Fast Forward | Frank Bourgeois US
Car Demand Planning | Car Prioiritization | Toan Do | Johnny Chi | Not Started |  |  |  |  | In Progress | 2026-04-17
Ops | Dispatch & Scheduling | Anna Svizhenko | Eric Estes | Not Started
| TO Allocation | Jingyi Chen | Frederick Yen | Not Started
| TO Annotation, Guidelines and Training | Elizabeth Busi |  | Not Started
| Exec Drives Scheduling | Jingyi Chen | Frederick Yen | Not Started
| Car Provisioning | Kellen Davies |  | Not Started | [5 empty] | 2026-04-27
| MTTF Provisioning | Kellen Davies
| US: Scaling PMB: HFE + AMO Highway | Jenny Liu | [6 empty] | Blocked | 2026-05-04 |  | Pending Test Requirements and Test Plan Review Ninad Alulkar US, Vinay Kumar Reddy Kaitha US.
In Car Testing Strategy | Test Plan & Strategy | Bruce Guo | Amol Wandile | In Process |  |  |  |  | Complete |  |  | [SIT] R18 Test Plan & Strategy Diversity plan aligning with V&V and DA
| Test Execution Plan | Renmin/Vinay/Ninad | [6 empty] | In Progress | 2026-04-27 |  | R18 [Carline][L2++ Safety][Pre-Merge] in progress
| Diversity Test Plan | Renmin/Vinay/Ninad | [6 empty] | In Progress | 2026-04-22 |  | R18 L2+ & HFE US Freeway Driving Validation Plan0
| Diverisity Test excution | Renmin/Vinay/Ninad | [6 empty] | Not Started | 2026-04-27 |  | rely on: 1 car allocation: ongoing check wtih Toan 2 Vip(R18.1.0) upgrade(4/27) 3 Feature complete(4/27)
| PMB Test Start in US & EU | Bruce Guo | [6 empty] | Complete | 2026-03-20
| IFORV | Dhiraj
| Maps | Clint May |  | Not Started
| Regions/Hubs | Bruce Guo | Amol Wandile | Not Started |  |  |  |  | In Progress |  |  | diversity plan align with V&V
Offline Testing | Digital Replay Component WFs | Kelly Clonts |  | Not Started |  |  |  |  | In Progress
| DIFORV | Gaurav Ahuja | Jisha Prakash | Not Started |  |  |  |  | In Progress
| AMO CLE | Kelly Clonts | Michael Kasa | Not Started |  |  |  |  | In Progress
| HCM | Kelly Clonts | James Schulmeister | Not Started |  |  |  |  | In Progress
| Perf Test Suote | Sai Gurrappadi
| Release WF | Gaurav Ahuja | Vikas Jethlya | Not Started
| SIL3 | Jay Cheng | Pradyotha Nori | Not Started
| MTTF Allocation | Houman Tavakoli | Sreekanth Vietla | Not Started |  |  |  |  | Complete
| MTTF Execution | Dhanakodi Prabhu | Rahul Bahirmal | [5 empty] | In Progress
| Car CI/STS Suite | Hunk Lin | Richard Lin | Not Started |  |  |  |  | Complete
| Car CI/STS Execution | Dhanakodi Prabhu | Rahul Bahirmal | [5 empty] | In Progress
Post Drive Gates | Perf | Sai Gurrappadi | Eli Feinberg | Not Started |  |  |  |  | In Progress
| DI/DQ | Karthik Bhardwaj |  | Not Started
| Exceptions | Thomas Rushton |  | Not Started
Triage | Tagging Definitions | Jason Xiao | [6 empty] | In Progress
KPI Tracking
In Progress
Tooling | Alfred | Hunk Lin |  | Not Started |  |  |  |  | Not Started
Test Studio
Quality Control (QC)
OPTIC
| Optic | Keshav Agarwal | [6 empty] | In Progress

## Sheet2 (hidden)
Features | Tasks | Subtasks | R17 | R18 | L3 | AML
HFE - Highway AMO
VIP
Platform Stability
PMB Builds
In Car Testing
In Car Testing Operations Planning
In Car Testing Strategy
Offline Testing
Post Drive Analysis
PMB Gating & Approval
Tooling
SILC - Highway AMO
VIP
Platform Stability
PMB Builds
In Car Testing
In Car Testing Operations Planning
In Car Testing Strategy
Offline Testing
Post Drive Analysis
PMB Gating & Approval
L2pp - AMO
VIP
Platform Stability
PMB Builds
In Car Testing
In Car Testing Operations Planning
In Car Testing Strategy
Offline Testing
Post Drive Analysis
PMB Gating & Approval
L2 Driving - L2p Planner
VIP
Platform Stability
PMB Builds
In Car Testing
In Car Testing Operations Planning
In Car Testing Strategy
Offline Testing
Post Drive Analysis
PMB Gating & Approval

## Branching
Branch Setup Requirements | Notes | PIC | Time to Implement | Needed before PMB Start?
GVS & Test Support | List of Required GVS Builds and config setup | Doug Seay US | 2d | Yes
GVS Compute Allocation | Expected test and build/number of CLs to merge | Sam Payne US | 2d | Yes
Alfred Setup | IBM, PBM, Automatic Vote Jobs, integration with DIFORV, MTTF (Alfred has a full checklist) | Hunk Lin CN | 1w | Yes
PMB Query Setup |  | Adam Watson US | 1d | Yes
QC Support | What do we need? | Udith Hegde US |  | Yes
Coverity and Code Coverage | What do we need? | Kivanc Temel US |  | Yes
MTTF Setup & Allocation | What configs/coding do we need and how many do we need? |  | 2d | Yes
Promotions Requirements |  | Adam Watson US | 1d | Yes
Gerrit Workflows | What votes, who has acces to votes, etc | Adam Watson US | 1d | Yes
AV Maintainer Support |  |  |  | Yes
DIFORV Setup | What tests, correct branch builds, correct api calls, etc |  |  | Yes
Other Test Studio Setup |  |  |  | Yes
AVBT Tooling | AVBT has a full checklist | Frank Bourgeois US | 1w | Yes
Branch Activation |  |  | 1d | Yes
CCB Process Definition |  | Ying Ying US | 2d | Yes
Per Feature Requirements
Test Coverage (DIFORV & MTTF) | Do we need to add additional tests and or update Tests | DA/Dev | 4d | Yes
DAG Updates | Are there any expected changes to the DAG? | Xiao Bo Team | 2d | Yes
Amends (if needed) | Are there any new amends to be used/updated | DA/Dev | 3d | Yes
Ops training (if needed) on expected behavior changes | Do we need to update operations training on new feature | Ops | 1w | Yes
Incompatibility issues (TRT10) | What are the potential incompatible issues and what is the plan to mitigate | Xiao Bo team | 2d | Yes
triage changes | Do we need to update Triage Layouts and tell the triage team about what is going on | DA/Dev | 3d | Yes
Region specific issues |  |  |  | Yes
Maps? |  |  |  | Yes
Test Plan updates | Is this feature already covered/exectued during regular testing, or do we need to update? |  |  | No
Impacts to KPIs and if we need modifications to them |  |  |  | No